## Sheet1
Date | Calendar Event / Deliverable | Deadline Type | Responsible Party
2026-10-26 | Finalize complaint, exhibits, civil cover sheet, and filing materials | Internal | Attorney / Paralegal
2026-10-29 | Attorney review and approval of complaint | Internal | Lead Attorney
2026-11-02 | File complaint and issue summons | Filing | Paralegal / Attorney
2026-11-04 | Complete service of process on Summit; obtain proof | Service | Process Server / Paralegal
2026-11-06 | File return of service and verify docket entries | Filing / QC | Paralegal
2026-11-11 | Confirm document preservation and client custodian interviews | Internal | Paralegal
2026-11-25 | Summit's answer or other authorized response due (assumes no extension or motion altering the deadline) | Responsive Pleading | Defense Counsel
2026-12-02 | Prepare preliminary witness, document, and damages disclosure lists | Internal | Paralegal
2026-12-09 | Parties' Rule 16 meet-and-confer deadline | Procedural | Both Counsel
2026-12-16 | Complete internal review of proposed initial disclosures | Internal | Attorney / Paralegal
2026-12-23 | Exchange initial disclosures | Procedural | Both Parties
2027-01-06 | File proposed case management order (assumed standard Rule 16) | Filing | Both Counsel
2027-01-13 | Case management conference | Hearing | Attorneys
2027-01-20 | Serve first requests for production and interrogatories | Discovery | Plaintiff's Counsel
2027-02-10 | Review collection progress and outstanding discovery | Internal | Paralegal
2027-02-19 | Review anticipated discovery responses and deficiencies | Internal | Attorney / Paralegal
2027-03-05 | Meet and confer regarding discovery deficiencies | Discovery | Both Counsel
2027-03-19 | Review supplemented productions and update evidence index | Internal | Paralegal
2027-04-12 | Deposition of Summit production manager (illustrative setting) | Deposition | Attorneys / Court Reporter
2027-04-26 | Deposition of Horizon procurement director (illustrative setting) | Deposition | Attorneys / Court Reporter
2027-05-14 | Discovery cutoff (hypothetical scheduling order) | Court Ordered | Both Parties
2027-06-21 | Dispositive motions deadline (hypothetical scheduling order) | Court Ordered | Attorneys
2027-08-09 | Exchange draft witness/exhibit lists and exhibits | Procedural | Both Counsel
2027-08-16 | Motions in limine deadline, absent contrary order | Procedural | Attorneys
2027-08-23 | Proposed trial management order due | Filing | Both Counsel
2027-09-13 | Final trial preparation and exhibit quality control | Internal | Attorney / Paralegal
2027-09-20 | Jury trial begins (hypothetical setting) | Trial | Trial Team